## Timeline
Event Title
Date
Time
Timeline
3+ Months Before Tasks | Responsibility | Due Date | Completed
Solidify location
Secure panelists and moderator
Secure livestream
2 Month Before Tasks | Responsibility | Due Date | Completed
Obtain event language from speaker
Edit event language (if needed)
Create Run of Show (ROS)
Gather invitee list
Create invitation
Submit Event Registration Form for Website Event Page and EventBrite
Schedule call with speakers to review ROS
Discuss ROS
Send Invitation #1
Secure speakers' travel
Create draft Day of Schedule (DOS)
Secure volunteers
1 Month Before Tasks | Responsibility | Due Date | Completed
Call with speakers to review ROS
Create Printed Program (if needed)
Send Invitation #2 (if needed based on RSVPs)
Create or gather PowerPoint Slides
Submit Swag Form (if needed)
Submit Event Prep form (30 days before)
1 Week Before Tasks | Responsibility | Due Date | Completed
Print Program (if needed)
Finalize DOS and email volunteer assignments
Send final reminder to attendees
Provide livestream link (if needed)
EVENT DAY
Post Event | Responsibility | Due Date | Completed
Send thank you to speakers
Send thank you to guests
Update budget
Debrief on event
Submit a post-event summary and photo for Wagner website and social media channels to wagner.communications@nyu.edu (if possible)

## Run of Show
Event Title
Date
Time
Run of Show
Time | Session | Speaker
0.72917 | Staff and Volunteer Arrival
0.75 | Doors Open
0.77014 | VOG to Audience: "Welcome to NYU Wagner, please take your seats and silence your cell phones. The program is about to begin."
0.77083 | PROGRAM BEGINS
| Welcome & Opening Remarks (5 minutes) | Speaker A
0.77431 | Moderator speaks and introduces panelists (3 minutes) | Moderator
0.77639 | Panel begins with moderator asking questions
0.81806 | Timekeeper - 5 minute warning
0.82153 | Moderator moves to Q&A from audience
Q&A (15 minutes)
0.83125 | Timekeeper - 1 minute warning (if needed)
0.83194 | Closing Remarks (2 minutes) | Moderator
0.83333 | PROGRAM ENDS
RECEPTION BEGINS
Cue music
0.85417 | RECEPTION ENDS

## Day of Schedule
Event Title
Date
Time
Day of Schedule
Time | Session | Speaker
5:00PM | Check Rudin room set up, place event signage, and provide guest list to security downstairs
0.71875 | Staff and Volunteer Arrival
0.72917 | Tech Run Through
Set Up Registration Table
5:45PM | Staff and Volunteers in Place
0.75 | Doors Open
0.77014 | VOG to Audience: "Welcome to NYU Wagner, please take your seats and silence your cell phones. The program is about to begin."
0.77083 | PROGRAM BEGINS
| Welcome & Opening Remarks (5 minutes) | Speaker A
0.77431 | Moderator speaks and introduces panelists (3 minutes) | Moderator
0.77639 | Panel begins with moderator asking questions
0.81806 | Timekeeper - 5 minute warning
0.82153 | Moderator moves to Q&A from audience
Q&A (15 minutes)
0.83125 | Timekeeper - 1 minute warning (if needed)
0.83194 | Closing Remarks (2 minutes) | Moderator
0.83333 | PROGRAM ENDS
RECEPTION BEGINS
Cue music
0.85417 | RECEPTION ENDS
Clean up any materials, return any tech items, and return signage stands

## Staff Volunteer Schedule
Event Title
Date
Staff Volunteer Schedule
|  | 17:00 | 17:30 | 17:45 | 18:30 | 19:00 | 19:30 | 20:00 | 20:30 | 21:00
1 | Staff Name
2
3
4
5
6
7
8
9
10

## Budget Sample
Event Name
Date
Budget as of Date
| Unit | Unit Cost | Cost | Total
Venue Booking | 1 | 350 | 350 | 350
Processing Fee | 1 | 3% | 10.5 | 10.5
Venue Total |  |  |  | 360.5
Lunch | 50 | 50 | 2500 | 2500
Beverages | 50 | 2.5 | 125 | 125
Delivery Fee | 1 | 50 | 50 | 50
Catering Total |  |  |  | 2675
AV | 1 | 350 | 350 | 350
AV Total |  |  |  | 350
Supplies Total | 1 | 100 | 100 | 100
Supplies Total |  |  |  | 100
Grand Total |  |  |  | 3485.5